## Sheet1
Question No. | Date Received | REFERENCE |  |  | QUESTION | GOVERNMENT RESPONSE | Posted on Amend No.
|  | Page | Section | Para.
1 | 2026-04-28 |  |  |  | Will any power supply lines being serviced by a panel need to be fully powered during the project timeframe?
2 | 2026-04-28 |  |  |  | Which panels (if any) are connected with or impacted by the existing Pink Shaver system? Who would the GC coordinate with for direction with the Pink Shaver system?
3 | 2026-04-28 | Attachment A Sect 01 3 f. |  |  | Please confirm no escorts are required for construction workers involved with the project?
4 | 2026-04-28 |  |  |  | Can a portion of the nearby parking area be used for a project laydown/storage/material yard?
5 | 2026-04-28 | Attachment M |  |  | Is the CMMC Certification required prior to bidding the Substation Switchgear Conversion project?
6 | 2026-04-28 |  |  |  | What is the allowed maximum amount of time a panel can be offline?
7 | 2026-04-28 |  |  |  | Will a back up generator be required to maintain power during panel shut downs?
8 | 2026-04-28 | SF 1442 |  | 11 | The SF 1442 indicates a performance period of 540 days. Considering the procurement and design phases, as well as the potential lead time in excess of 60 weeks (as discussed in the site walk), the 77 week project schedule is therefore not practical. Considering long led times, design time, wether delays, as well as general construction, it is requested NAVFAC consider an 800 day performance period.
9 | 2026-04-28 |  |  |  | Is it the intention of the project to maintain the wooden storage structure presently on the site in it’s present condition?
2 | 2026-04-22 | 11 | 1 33 00 .05 20 | 1.2 d | Please confirm HVAC Testing, Adjusting, and Balancing submittals are required.
10 | 2026-04-28 | 8 | 1 20 00 | 1.3 | Please confirm there is no HVAC work as indicated in the Budget Management paragraph. This section is not used.
11 | 2026-04-28 | 31 | 01 74 19 | 6 | Please confirm the line D30 HVACD40 Fire Protection Systems is not aused in this project
12 | 2026-04-28
13 | 2026-04-28
14 | 2026-04-28
15 | 2026-04-28
16 | 2026-04-28
17 | 2026-04-28
18 | 2026-04-28
19 | 2026-04-28
20 | 2026-04-28