## Bid Summary Sheet
ENCON CORPORATION
N4008023RX017 Exchange Substation Switch Gear
| Project Name: |  | Exchange Substation Switch Gear
| Bid No: |  | N4008023RX017
| Bid Date: |  | 2026-05-14 | 2 PM EST | Submission: | PIEE
| Amendments: |  | 0
| Bid Bond Required (Y/N) ?: |  | Yes
| Performance Period: |  | 525 | Days
| On Site: |  | 210 | Days
| Project Magnitude: |  | $1M - $5M
| General Requirements | [11 empty] | Demo Door (1 items)
| Description | Qty | UOM | Labor | Burden | Material | Taxes | Equipment | Taxes | Subcontractor | Total |  | Demo TP Stall (5 items)
Demo Urinal (2 items)
| Project Manager | 18 | weeks | 2800 | 840 | 0 | 0 | 0 | 0 | 0 | 65520 |  | Infill 21sf (1 items)
| Site Superintendent / QCM | 28 | weeks | 2700 | 810 | 0 | 0 | 0 | 0 | 0 | 98280 |  | Infill 35sf (1 items)
| SSHO | 28 | weeks | 2700 | 810 | 0 | 0 | 0 | 0 | 0 | 98280 | Possibly Removed | Infill 35sf (1 items)
| Asst Superintendent | 0 | weeks | 2500 | 750 | 0 | 0 | 0 | 0 | 0 | 0 |  | Replace Air Supply and Recalc CFM (2 items)
| Labor Foreman | 0 | weeks | 2000 | 600 | 0 | 0 | 0 | 0 | 0 | 0
| Project Engineer | 0 | weeks | 2000 | 600 | 0 | 0 | 0 | 0 | 0 | 0
| Estimator | 0 | month | 300 | 90 | 0 | 0 | 0 | 0 | 0 | 0
| Project Accountant | 0 | weeks | 1900 | 570 | 0 | 0 | 0 | 0 | 0 | 0
| Project Administrator | 0 | weeks | 1900 | 570 | 2 | 0.12 | 0 | 0 | 0 | 0
| Scheduler | 0 | weeks | 1900 | 570 | 0 | 0 | 0 | 0 | 0 | 0
| Dumpsters | 12 | Pulls | 0 | 0 | 0 | 0 | 450 | 27 | 0 | 5724
| Temporary Toilets | 7 | Mo | 0 | 0 | 0 | 0 | 500 | 30 | 0 | 3710
| Miscellaneous Materials | 1 | Ea | 0 | 0 | 2500 | 150 | 0 | 0 | 0 | 2650
| Testing and Inspections | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000
| Onsite Lock Up | 6 | Month | 0 | 0 | 500 | 30 | 0 | 0 | 0 | 3180
| Site Clean Up | 1 | weeks | 1600 | 560 | 0 | 0 | 0 | 0 | 0 | 2160
| Miscellaneous Materials | 1 | LS | 0 | 0 | 1000 | 60 | 0 | 0 | 0 | 1060
| Jobsite Trailer (Add $500 Travel) | 7 | months | 0 | 0 | 600 | 36 | 0 | 0 | 0 | 4452
| WIFI | 0 | months | 0 | 0 | 80 | 4.8 | 0 | 0 | 0 | 0
| Office Supplies | 0 | month | 0 | 0 | 200 | 12 | 0 | 0 | 0 | 0
| Temp Fence | 6 | month | 0 | 0 | 300 | 18 | 0 | 0 | 0 | 1908
| Project Bulletin Board | 0 | LS | 0 | 0 | 250 | 15 | 0 | 0 | 0 | 0
| Design Fees | 200000 | allow | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | Need Budget from Setti
| Site Survey | 1 | allow | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500
| Design Contingency | 1 | allow | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
[7 empty] | Total General Expenses: |  |  |  | 549424
Subcontractor Trades
Division # | Description
26 | Electrical Switch Gear Work | 1 | LS | [6 empty] | 454600 | 454600
[7 empty] | Subcoontractor Trades |  |  |  | 454600
[7 empty] | Project Subtotal: |  |  |  | 1004024
[7 empty] | Overhead |  | 8 | % | 80321.92
[7 empty] | Subtotal |  |  |  | 1084345.92
[7 empty] | Profit |  | 7 | % | 75904.2144
[7 empty] | Subtotal |  |  |  | 1160250.1344
[7 empty] | Bond |  | 1.5 | % | 17403.752
[7 empty] | Sub Total |  |  |  | 1177653.8864
[7 empty] | Estimate Total: |  |  |  | 1177000

## Div 26 Electrical
Exchange Substation Switch Gear
Turner VA Corporation
Electrical |  |  |  | Robie
| ESTIMATE |  |  | (p)703.630.4727
Checklist
Scope:
Plans & Specs
Electrical |  |  |  | Bidding
Coordinate shut down of Electrical Panels | 16 | 100 | 1600
Supply new Switch Gear | 16 | 3000 | 48000
Coordinate Intregation with Pink Shaver system | 16 | 100 | 1600
Install new Switch Gear | 3360 | 100 | 336000
Electrical Wiring | 3200 | 7 | 22400
Forklift | 1 | 6400 | 6400
Replace Fence Section | 1 | 2000 | 2000
Utility Concrete Pads | 20 | 500 | 10000
Underground Duct Bank |  |  |  | Bidding
Underground Duct Bank | 100 | 200 | 20000
Landscape Repair | 1 | 5000 | 5000
Backhoe | 2 | 800 | 1600
|  |  | 454600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BID FORM NUMBERS |  | Proposal Used
Estimate | 454600 | 454600
Turner VA Corporation | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
Total this Page |  | 454600
Note on B1: Enter Project Name Here